## Iteration 1 Plan
Iteration Plan 1
Project
Team Names: | Team #2
Team Number: | Bin Yang, Romnick Zinampan, James Arand
1. What deliverables did the team plan to complete by the end of the iteration? Refer to your Project Plan submitted in Week 3 to determine which items should be completed. Please note that dates may change as the Iterations continue and various issues arise. Did this Iteration include other work items such as setting up a development environment or bug fixes in the Iteration backlog list?
Number | Description | Responsibility (Initials) | Project Plan adherence?
101 | Database: Database Design | BY
102 | Database: Deployed to local SQL Server DB (Move to online DB later) | BY
103 | UC07: User registration | BY, JA, RZ
104 | UC01: User login | BY, JA, RZ
105 | Visual Design: Home Page, Task Page, Creation Page, Edit Page, Policy Page, Login Page, Register Page | BY, JA, RZ
106 | View: Home Page, Task Page, Creation Page, Edit Page, Policy Page, Login Page, Register Page | BY, JA, RZ
107 | UC02-04: Task CRUD operations | BY, JA, RZ
108 | UC06: Tasks are categorized and showed as expected | BY, JA, RZ
109 | Diagrams: Use case diagrams and Descriptions | BY, JA
110 | Diagrams: Domain class diagram, system sequence diagram, statechart diagram | BY, JA, RZ
2. Did the team identify the architecture (hardware/software/platform/solution design) early? Was there a architecture owner assigned?
List of architecture being used | Concerns (current and potential) | Owner Assigned (Initials)
HTML, CSS, JavaScript | Well known | BY, RZ, JA
C# | Well known | BY, RZ, JA
ASP.NET core | Learnt in the past courses | BY, RZ, JA
Bootstrap | Need to develop | BY, RZ, JA
SQL Server | Learnt in the past courses | BY, RZ, JA
MS Azure SQL Databases | New solution | BY, RZ, JA
Git, Github | New solution | BY, RZ, JA
Visual Paradigm | Learnt in the past courses | BY, RZ, JA
JustinMind | Learnt in the past courses | BY, RZ, JA
3. Did your team visually track your progress by using tools such as Microsoft Project, SharePoint, Trello, etc.? Explain why you choose this tool.
Tracking Software Used | Why?
Planner | Easy to setup, built-in tool in teams that's shared with team members
Microsoft Project | (Not using anymore) Suggested by the course instructions
The point of the Iteration Plan is to have a goal set from the backlog. Iteration Plan and backlog are submitted prior to each iteration. Iteration Plans can repeat work items if feedback is provided by the client that further updates are required for a deliverable. Each iteration should have a working code demostration.
Note: These guiding questions are not meant to be exhaustive. Each team is responsible for the delivery of a workable solution.

## Agile Backlog 1
Iteration 1 Backlog
Notes Iteration 1, all numbers begin with 101 and continue upward. In Iteration 2, all numbers start with 201 and continue upward. In Iteration 3, all numbers begin with 301 and continue upward. Start number column from 101. Outside requirements such as Inception pieces or other requirements are numbered 1-100. PD = Person Day and the number of hours they will spend on a task. Only high-priority items are prioritized, assigned to iteration, and estimated.
Number | Description | PD est. | By
High Priority (light green)
Iteration 1
101 | Database: Database Design | 1 | BY
102 | Database: Deployed to local SQL Server DB (Move to online DB later) | 1 | BY
103 | UC07: User registration | 2 | BY, JA, RZ
104 | UC01: User login | 2 | BY, JA, RZ
105 | Visual Design: Home Page, Task Page, Creation Page, Edit Page, Policy Page, Login Page, Register Page | 2 | BY, JA, RZ
106 | View: Home Page, Task Page, Creation Page, Edit Page, Policy Page, Login Page, Register Page | 4 | BY, JA, RZ
107 | UC02-04: Task CRUD operations | 2 | BY, JA, RZ
108 | UC06: Tasks are categorized and showed as expected | 1 | BY, JA, RZ
109 | Diagrams: Use case diagrams and Descriptions | 1 | BY, JA
110 | Diagrams: Domain class diagram, system sequence diagram, statechart diagram | 1 | BY, JA, RZ
111
…
Iteration 2
Iteration 3
| Medium Priority (light blue) |  |  | Note: assigned medium and low tasks are prioritized but not yet assigned to iteration, nor estimated.
Design: Calendar Page
| Prototype: Do a demo of a dynamic calendar as an experiment for upcoming iterations |  | BY
Low Priority (pink)

## Agile Release Summary 1
Iteration 1: Release Plan Summary
Note The top row lists Number, Feature/Requirement, Inception, Iterations 1, 2, and 3, and Transition. The Number and Feature/Requirements column information is provided in your backlog. The numbers and task must match the backlog information. Once this information is inputted into your release summary chart your team will determine what iteration the tasks will be completed and how many hours are needed to complete each task. Each group should expect to work 9 person-days (PD) per week. A reminder that 1 person day is equal to 4 person hours.
Colour Coding
Inception and Other Requirements (gray) | Iteration 1 (orange) | Iteration 2 (light Blue) | Iteration 3 (light yellow) | Transition (light green)
Number | Feature / Requirement | Inception PD | Iteration #1 PD | Iteration #2 PD | Iteration #3 PD | Transition PD
|  | Due: | Due: | Due: | Due: | Due:
1 | Finish inception documents | 6
101 | Database: Database Design |  | 1
102 | Database: Deployed to local SQL Server DB (Move to online DB later) |  | 1
103 | UC07: User registration |  | 2
104 | UC01: User login |  | 2
105 | Visual Design: Home Page, Task Page, Creation Page, Edit Page, Policy Page, Login Page, Register Page |  | 2
106 | View: Home Page, Task Page, Creation Page, Edit Page, Policy Page, Login Page, Register Page |  | 4
107 | UC02-04: Task CRUD operations |  | 2
108 | UC06: Tasks are categorized and showed as expected |  | 1
109 | Diagrams: Use case diagrams and Descriptions |  | 1
110 | Diagrams: Domain class diagram, system sequence diagram, statechart diagram |  | 1
Work Effort in Person Days (PD) 1 PD hour equals 4 hours |  | 24 | 68 | 0 | 0 | 0
Total Project Hours |  | 92

## Iteration 2 Plan
Iteration Plan 2
Project
Team Names:
Team Number:
1. What deliverables did the team plan to complete by the end of the iteration? Refer to your Project Plan submitted in Week 3 to determine which items should be completed. Please note that dates may change as the Iterations continue and various issues arise. Did this Iteration include other work items such as setting up a development environment or bug fixes in the Iteration backlog list?
Number | Description | Responsibility (Initials) | Project Plan adherence?
201 | UC02-04: Task CRUD operations - Refine | BY, JA, RZ
202 | UC06: Tasks are categorized and showed as expected - Refine | BY, JA, RZ
203 | Diagrams: Use case diagrams and Descriptions | BY, JA
204 | Diagrams: Domain class diagram, system sequence diagram, statechart diagram | BY, JA, RZ
205 | Website Design: Color Plan, Style, Logo, etc. | BY, JA, RZ
206 | Bootstrap study & integration | BY, JA, RZ
207 | Views: Webpage refine | BY, JA, RZ
208 | Dynamic Timetable view Implementation | BY, JA, RZ
209 | View: Home Page Task Chart and Pie Chart implementation | BY, JA, RZ
2. Did the team identify the architecture (hardware/software/platform/solution design) early? Was there a architecture owner assigned?
List of architecture being used | Concerns (current and potential) | Owner Assigned (Initials)
HTML, CSS, JavaScript | Well known | BY, RZ, JA
C# | Well known | BY, RZ, JA
ASP.NET core | Learnt in the past courses | BY, RZ, JA
Bootstrap | Need to develop | BY, RZ, JA
SQL Server | Learnt in the past courses | BY, RZ, JA
MS Azure SQL Databases | New solution | BY, RZ, JA
Git, Github | New solution | BY, RZ, JA
Visual Paradigm | Learnt in the past courses | BY, RZ, JA
Visual Studio | Well known | BY, RZ, JA
3. Is your team still using the tracking software for your project? Are there any significant timeline changes to your project?
Tracking Software | Progress & Updates
Planner | Easy to setup, built-in tool in teams that's shared with team members
The point of the Iteration Plan is to have a goal set from the backlog. Iteration Plan and backlog are submitted prior to each iteration. Iteration Plans can repeat work items if feedback is provided by the client that further updates are required for a deliverable. Each iteration should have a working code demostration.
Note: These guiding questions are not meant to be exhaustive. Each team is responsible for the delivery of a workable solution.

## Agile Backlog 2
Iteration 2 Backlog
Notes Iteration 1, all numbers begin with 101 and continue upward. In Iteration 2, all numbers start with 201 and continue upward. In Iteration 3, all numbers begin with 301 and continue upward. Start number column from 201. Outside requirements such as Inception pieces or other requirements are numbered 1-100. PD = Person Day and the number of hours they will spend on a task. Only high-priority items are prioritized, assigned to iteration, and estimated.
Number | Description | PD est. | By
High Priority
Iteration 1
201 | UC02-04: Task CRUD operations - Refine | 2 | BY, JA, RZ
202 | UC06: Tasks are categorized and showed as expected - Refine | 3 | BY, JA, RZ
203 | Diagrams: Use case diagrams and Descriptions | 1 | BY, JA
204 | Diagrams: Domain class diagram, system sequence diagram, statechart diagram | 1 | BY, JA, RZ
205 | Website Design: Color Plan, Style, Logo, etc. | 3 | BY, JA, RZ
206 | Bootstrap study & integration | 3 | BY, JA, RZ
207 | Views: Webpage refine | 4 | BY, JA, RZ
208 | Dynamic Timetable view Implementation | 4 | BY, JA, RZ
209 | View: Home Page Task Chart and Pie Chart implementation | 2 | BY, JA, RZ
Iteration 2
Iteration 3
Medium Priority
221 | Feature: Small ChatGPT add-on feature that provides plan to finish tasks | 4 | BY, JA, RZ
Low Priority

## Agile Release Summary 2
Iteration 2: Release Plan Summary
Note The top row lists Number, Feature/Requirement, Inception, Iterations 1, 2, and 3, and Transition. The Number and Feature/Requirements column information is provided in your backlog. The numbers and tasks must match the backlog information. Once this information is inputted into your release summary chart your team will determine what iteration the tasks will be completed and how many hours are needed to complete each task. Each group should expect to work 9 person-days (PD) per week. A reminder that 1 person day is equal to 4 person hours.
Colour Coding
Inception and Other Requirements (gray) | Iteration 1 (orange) | Iteration 2 (light Blue) | Iteration 3 (light yellow) | Transition (light green)
Number | Feature / Requirement | Inception | Iteration #1 | Iteration #2 | Iteration #3 | Transition
|  | Due: | Due: | Due: | Due: | Due:
1 | Finish inception documents | 6
101 | Database: Database Design |  | 1
102 | Database: Deployed to local SQL Server DB (Move to online DB later) |  | 1
103 | UC07: User registration |  | 2
104 | UC01: User login |  | 2
105 | Visual Design: Home Page, Task Page, Creation Page, Edit Page, Policy Page, Login Page, Register Page |  | 2
106 | View: Home Page, Task Page, Creation Page, Edit Page, Policy Page, Login Page, Register Page |  | 4
107 | UC02-04: Task CRUD operations |  | 2
108 | UC06: Tasks are categorized and showed as expected |  | 1
109 | Diagrams: Use case diagrams and Descriptions |  | 1
110 | Diagrams: Domain class diagram, system sequence diagram, statechart diagram |  | 1
201 | UC02-04: Task CRUD operations - Refine |  |  | 2
202 | UC06: Tasks are categorized and showed as expected - Refine |  |  | 3
203 | Diagrams: Use case diagrams and Descriptions |  |  | 1
204 | Diagrams: Domain class diagram, system sequence diagram, statechart diagram |  |  | 1
205 | Website Design: Color Plan, Style, Logo, etc. |  |  | 3
206 | Bootstrap study & integration |  |  | 3
207 | Views: Webpage refine |  |  | 4
208 | Dynamic Timetable view Implementation |  |  | 4
209 | View: Home Page Task Chart and Pie Chart implementation |  |  | 2
Work Effort in Person Days (PD) 1 PD hour equals 4 hours |  | 24 | 68 | 92 | 0 | 0
Total Project Hours |  | 184

## Iteration 3 Plan
Iteration Plan 3
Project
Team Names:
Team Number:
1. What deliverables did the team plan to complete by the end of the iteration? Refer to your Project Plan submitted in Week 3 to determine which items should be completed. Please note that dates may change as the Iterations continue and various issues arise. Did this Iteration include other work items such as setting up a development environment or bug fixes in the Iteration backlog list?
Number | Description | Responsibility (Initials) | Project Plan adherence?
2. Did the team identify the architecture (hardware/software/platform/solution design) early? Was there a architecture owner assigned?
List of architecture being used | Concerns (current and potential) | Owner Assigned (Initials)
3. Is your team still using the tracking software for your project? Are there any significant timeline changes to your project?
Tracking Software | Progress & Updates
The point of the Iteration Plan is to have a goal set from the backlog. Iteration Plan and backlog are submitted prior to each iteration. Iteration Plans can repeat work items if feedback is provided by the client that further updates are required for a deliverable. Each iteration should have a working code demostration.
Note: These guiding questions are not meant to be exhaustive. Each team is responsible for the delivery of a workable solution.

## Agile Backlog 3
Iteration 3 Backlog
Notes Iteration 1, all numbers begin with 101 and continue upward. In Iteration 2, all numbers start with 201 and continue upward. In Iteration 3, all numbers begin with 301 and continue upward. Start number column from 201. Outside requirements such as Inception pieces or other requirements are numbered 1-100. PD = Person Day and the number of hours they will spend on a task. Only high-priority items are prioritized, assigned to iteration, and estimated.
Number | Description | PD est. | By
High Priority
Iteration 1
Iteration 2
Iteration 3
Medium Priority
Low Priority

## Agile Release Summary 3
Iteration 3: Release Plan Summary
Note The top row lists Number, Feature/Requirement, Inception, Iterations 1, 2, and 3, and Transition. The Number and Feature/Requirements column information is provided in your backlog. The numbers and task must match the backlog information. Once this information is inputted into your release summary chart your team will determine what iteration the tasks will be completed and how many hours are needed to complete each task. Each group should expect to work 9 person-days (PD) per week. A reminder that 1 person day is equal to 4 person hours.
Colour Coding
Inception and Other Requirements (gray) | Iteration 1 (orange) | Iteration 2 (light Blue) | Iteration 3 (light yellow) | Transition (light green)
Number | Feature / Requirement | Inception | Iteration #1 | Iteration #2 | Iteration #3 | Transition
|  | Due: | Due: | Due: | Due: | Due:
Work Effort in Person Days (PD) 1 PD hour equals 4 hours |  | 0 | 0 | 0 | 0 | 0
Total Project Hours |  | 0